## Weekly schedule planner
(Fake News Detector Web App Utilizing ML Models)
[6 empty] | Week of: |  |  | 2025-10-06
Weekly objectives |  |  |  |  | To do items | [7 empty] | Deadlines this week
Establish project foundation and organize initial resources | [5 empty] | Define detailed project goals and success criteria
Create user personas and use case examples
Collect initial datasets of labeled news articles (reliable/unreliable)
Set up version control system (Git repository)
Establish communication plan and meeting schedule for the team
Draft initial project timeline and milestone plan
06 | Monday | 07 | Tuesday | 08 | Wednesday |  | 09 | Thursday |  | 10 |  | Friday | 11 | Saturday | 12 |  | Sunday
| October |  | October |  | October |  |  | October |  |  |  | October |  | October |  |  | October
[11 empty] | Meeting Times |  |  |  |  | Meeting Times
Notes

## Weekly schedule planner (2)
Engineering Studio (Fake News Detector Web App Utilizing ML Models)
[6 empty] | Week of: |  |  | 2025-10-13
Weekly objectives |  |  |  |  | To do items | [7 empty] | Deadlines this week
Prepare and analyze datasets to inform model development | [5 empty] | Clean and preprocess datasets (remove duplicates, fix formatting)
Label articles into defined categories (reliable, unreliable, unknown)
Conduct exploratory data analysis (class distribution, word frequencies)
Research relevant NLP techniques for fake news detection
Design initial machine learning pipeline architecture document
13 | Monday | 14 | Tuesday | 15 | Wednesday |  | 16 | Thursday |  | 17 |  | Friday | 18 | Saturday | 19 |  | Sunday
| October |  | October |  | October |  |  | October |  |  |  | October |  | October |  |  | October
[11 empty] | Meeting Times |  |  |  |  | Meeting Times
Notes

## Weekly schedule planner (3)
Engineering Studio (Fake News Detector Web App Utilizing ML Models)
[6 empty] | Week of: |  |  | 2025-10-20
Weekly objectives |  |  |  |  | To do items | [7 empty] | Deadlines this week
[6 empty] | Implement baseline ML classification model (using algorithms like logistic regression or random forest) | [6 empty] | Presentation on Thursday
Build initial machine learning model and backend API framework | [5 empty] | Integrate basic NLP preprocessing (tokenization, stopword removal, vectorization)
Train and validate model performance (accuracy, precision, recall)
Develop backend REST API to receive article input and return predictions
Document API endpoints and expected data formats
20 | Monday | 21 | Tuesday | 22 | Wednesday |  | 23 | Thursday |  | 25 |  | Friday | 25 | Saturday | 26 |  | Sunday
| October |  | October |  | October |  |  | October |  |  |  | October |  | October |  |  | October
[11 empty] | Meeting Times |  |  |  |  | Meeting Times
Notes

## Weekly schedule planner (4)
Engineering Studio (Fake News Detector Web App Utilizing ML Models)
[6 empty] | Week of: |  |  | 2025-10-27
Weekly objectives |  |  |  |  | To do items | [7 empty] | Deadlines this week
Build simple user interface supporting paste, file upload, and URL input
Connect frontend input forms to backend API calls
Develop a functional frontend prototype and connect to backend | [5 empty] | Display classification results with confidence scores in UI
Collect informal feedback from team on usability and UI clarity
Identify frontend improvements based on feedback
27 | Monday | 28 | Tuesday | 29 | Wednesday |  | 30 | Thursday |  | 31 |  | Friday | 1 | Saturday | 2 |  | Sunday
| October |  | October |  | October |  |  | October |  |  |  | October |  | November |  |  | November
[11 empty] | Meeting Times |  |  |  |  | Meeting Times
Notes

## Weekly schedule planner (5)
Engineering Studio (Fake News Detector Web App Utilizing ML Models)
[6 empty] | Week of: |  |  | 2025-11-03
Weekly objectives |  |  |  |  | To do items | [7 empty] | Deadlines this week
Improve model accuracy and implement confidence-based output classification | [5 empty] | Expand training dataset with additional labeled articles
Retrain and fine-tune ML model using updated data
Add logic to classify outputs as reliable, unreliable, or requires further review via confidence thresholds
Create logging and error tracking system for backend predictions
Optimize backend for handling concurrent requests
3 | Monday | 4 | Tuesday | 5 | Wednesday |  | 6 | Thursday |  | 7 |  | Friday | 8 | Saturday | 9 |  | Sunday
| November |  | November |  | November |  |  | November |  |  |  | November |  | November |  |  | November
[11 empty] | Meeting Times |  |  |  |  | Meeting Times
Notes

## Weekly schedule planner (6)
Engineering Studio (Fake News Detector Web App Utilizing ML Models)
[6 empty] | Week of: |  |  | 2025-11-10
Weekly objectives |  |  |  |  | To do items | [7 empty] | Deadlines this week
Enhance NLP features and establish feedback loop for iterative learning | [5 empty] | Integrate advanced NLP features such as semantic similarity and sentiment analysis
Enhance linguistic feature extraction (e.g., hedging, sensationalism indicators)
Design and implement UI feedback system for users to flag incorrect results
Develop backend storage and processing for user feedback data
Plan incremental learning strategy using feedback for future model updates
10 | Monday | 11 | Tuesday | 12 | Wednesday |  | 13 | Thursday |  | 14 |  | Friday | 15 | Saturday | 16 |  | Sunday
| November |  | November |  | November |  |  | November |  |  |  | November |  | November |  |  | November
[11 empty] | Meeting Times |  |  |  |  | Meeting Times
Notes

## Weekly schedule planner (7)
Engineering Studio (Fake News Detector Web App Utilizing ML Models)
[6 empty] | Week of: |  |  | 2025-11-17
Weekly objectives |  |  |  |  | To do items | [7 empty] | Deadlines this week
Make app mobile-friendly or web application and add URL article extraction capability | [5 empty] | Refactor frontend for responsive design (mobile and tablet support)
Implement article content extraction from URLs using web scraping tools/APIs
Test complete input-to-output workflow via URL, text, and file inputs on multiple devices
Draft preliminary user documentation explaining features and usage
Begin compiling technical documentation for system components
17 | Monday | 18 | Tuesday | 19 | Wednesday |  | 20 | Thursday |  | 21 |  | Friday | 22 | Saturday | 23 |  | Sunday
| November |  | November |  | November |  |  | November |  |  |  | November |  | November |  |  | November
[11 empty] | Meeting Times |  |  |  |  | Meeting Times

## Weekly schedule planner (8)
Engineering Studio (Fake News Detector Web App Utilizing ML Models)
[6 empty] | Week of: |  |  | 2025-11-24
Weekly objectives |  |  |  |  | To do items | [7 empty] | Deadlines this week
Conduct comprehensive user testing and analyze system performance | [5 empty] | Recruit representative users (students, educators, journalists) for testing
Collect qualitative feedback on UI/UX and perceived classification accuracy
Perform quantitative evaluation of model results on new test datasets
Identify and fix bugs or usability issues discovered in user testing
Adjust model classification thresholds and UI elements based on feedback
Update all documentation to incorporate test-phase findings
24 | Monday | 25 | Tuesday | 26 | Wednesday |  | 27 | Thursday |  | 28 |  | Friday | 29 | Saturday | 30 |  | Sunday
| November |  | November |  | November |  |  | November |  |  |  | November |  | November |  |  | November
[11 empty] | Meeting Times |  |  |  |  | Meeting Times
Notes

## Weekly schedule planner (9)
Engineering Studio (Fake News Detector Web App Utilizing ML Models)
[6 empty] | Week of: |  |  | 2025-12-01
Weekly objectives |  |  |  |  | To do items | [7 empty] | Deadlines this week
Finalize system for deployment and prepare presentation materials | [5 empty] | Retrain model with full dataset including feedback data
Polish frontend UI for better visual design and user experience
Set up deployment infrastructure (hosting, server configuration, SSL, domain)
Perform security and load testing in staging environment
Prepare demo scripts and presentation slides for project showcase
Finalize complete project and user documentation
1 | Monday | 2 | Tuesday | 3 | Wednesday |  | 4 | Thursday |  | 5 |  | Friday | 6 | Saturday | 7 |  | Sunday
| December |  | December |  | December |  |  | December |  |  |  | December |  | December |  |  | December
[11 empty] | Meeting Times |  |  |  |  | Meeting Times
Notes

## Weekly schedule planner (10)
Engineering Studio (Fake News Detector Web App Utilizing ML Models)
[6 empty] | Week of: |  |  | 2025-12-08
Weekly objectives |  |  |  |  | To do items | [7 empty] | Deadlines this week
Deploy application and complete project reporting | [5 empty] | Launch web app on production server
Conduct live environment testing and fix any emergent issues
Provide support for early users and gather post-launch feedback
Compile and submit the final project report and presentation
Hold project retrospective and plan next steps for maintenance or improvements
8 | Monday | 9 | Tuesday | 10 | Wednesday |  | 11 | Thursday |  | 12 |  | Friday | 13 | Saturday | 14 |  | Sunday
| December |  | December |  | December |  |  | December |  |  |  | December |  | December |  |  | December
[11 empty] | Meeting Times |  |  |  |  | Meeting Times
Notes